PROJECT PLANNING PHASE

Automated Network Request Management in ServiceNow

| Field | Details |
| --- | --- |
| Date | 13 September 2026 |
| Team ID |  |
| Project Name | Automated Network Request Management in ServiceNow |

# Project Planning Overview

The project planning defines the product backlog, user stories, estimation, sprint schedule, project tracking, velocity and burndown for the Automated Network Request Management solution in ServiceNow. The plan covers the complete implementation lifecycle and is scheduled for final completion on 19 September 2026.

# Product Backlog, Sprint Planning, Stories and Estimation

The following backlog converts the required network request functionality into user stories and implementation tasks. Story points represent relative effort and are used to distribute work across the planned sprints.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Requirement Analysis | USN-1 | As a requester, I can submit a standardized network service request with the required information. | 3 | High |
| Sprint-1 | Requirement Analysis | USN-2 | As an administrator, I can define the required request information and approval requirements. | 2 | High |
| Sprint-1 | Requirement Analysis | USN-3 | As a project team member, I can document user needs, functional requirements and non-functional requirements. | 3 | High |
| Sprint-1 | Project Planning | USN-4 | As a project team member, I can create the product backlog, sprint schedule and effort estimates. | 2 | Medium |
| Sprint-2 | Request Data & Backend | USN-5 | As an administrator, I can configure the Network Request data structure and request fields. | 4 | High |
| Sprint-2 | Request Data & Backend | USN-6 | As an administrator, I can configure reference, choice and mandatory fields for network requests. | 3 | High |
| Sprint-2 | Workflow Automation | USN-7 | As an administrator, I can configure approval and fulfilment workflow automation. | 4 | High |
| Sprint-2 | Workflow Automation | USN-8 | As a fulfilment team member, I can receive an automatically generated fulfilment task. | 2 | High |
| Sprint-3 | Service Catalog | USN-9 | As a requester, I can access the Network Request catalog item through the Service Portal. | 3 | High |
| Sprint-3 | Request Form | USN-10 | As a requester, I can enter network request information using configured catalog variables. | 3 | High |
| Sprint-3 | Requester Information | USN-11 | As a requester, I can select a user and automatically populate related requester information. | 3 | Medium |
| Sprint-3 | Dynamic Form Behaviour | USN-12 | As a requester, I can see additional fields only when the selected request option requires them. | 3 | High |
| Sprint-4 | Testing | USN-13 | As a tester, I can validate successful and invalid network request submissions. | 3 | High |
| Sprint-4 | Workflow Testing | USN-14 | As a tester, I can verify approval, fulfilment task creation, assignment and status updates. | 3 | High |
| Sprint-4 | Security | USN-15 | As an administrator, I can verify that request and approval information is accessible only to authorized users. | 3 | High |
| Sprint-4 | Defect Handling | USN-16 | As a project team member, I can record defects, corrections and test results. | 2 | Medium |
| Sprint-5 | Deployment | USN-17 | As a project team member, I can prepare the completed configuration for final deployment. | 3 | High |
| Sprint-5 | Documentation | USN-18 | As a project team member, I can prepare configuration evidence and complete project documentation. | 3 | High |
| Sprint-5 | Demonstration | USN-19 | As a project team member, I can demonstrate the complete network request lifecycle. | 3 | High |
| Sprint-5 | Final Delivery | USN-20 | As a project team member, I can complete the final presentation and project submission. | 2 | High |

# Sprint Schedule

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 10 | 2 Days | 06 Sep 2026 | 07 Sep 2026 | 10 | 07 Sep 2026 |
| Sprint-2 | 13 | 3 Days | 08 Sep 2026 | 10 Sep 2026 | 13 | 10 Sep 2026 |
| Sprint-3 | 12 | 3 Days | 11 Sep 2026 | 13 Sep 2026 | 12 | 13 Sep 2026 |
| Sprint-4 | 11 | 3 Days | 14 Sep 2026 | 16 Sep 2026 | 11 | 16 Sep 2026 |
| Sprint-5 | 11 | 3 Days | 17 Sep 2026 | 19 Sep 2026 | 11 | 19 Sep 2026 |

Total planned story points: 57. Final project completion and release date: 19 September 2026.

# Project Tracker

| Sprint | Planned Work | Start Date | End Date | Story Points | Completion |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Requirements, user stories, backlog and estimation | 06 Sep 2026 | 07 Sep 2026 | 10 | Completed |
| Sprint-2 | Backend data structure, fields and workflow automation | 08 Sep 2026 | 10 Sep 2026 | 13 | Completed |
| Sprint-3 | Catalog item, variables, requester information and dynamic UI | 11 Sep 2026 | 13 Sep 2026 | 12 | Completed |
| Sprint-4 | Testing, workflow validation, defect handling and security checks | 14 Sep 2026 | 16 Sep 2026 | 11 | Completed |
| Sprint-5 | Deployment preparation, documentation and final demonstration | 17 Sep 2026 | 19 Sep 2026 | 11 | Completed |

# Velocity

Velocity is the amount of story-point work completed in an iteration. Based on the planned project backlog, 57 story points are distributed across 5 sprints.

Average Velocity = Total Story Points / Number of Sprints = 57 / 5 = 11.4 story points per sprint

# Burndown Chart

The burndown chart shows the planned reduction of remaining work across the sprint schedule. The project reaches zero remaining story points on the final completion date.

# Project Completion

The planned project work is completed by the end of Sprint-5 on 19 September 2026. The final deliverable includes the configured ServiceNow network request solution, validated request lifecycle, testing and security evidence, documentation and final demonstration.